## Slide 1: MakerSat-0 Northwest Nazarene University
 |  | Mission Description |  | 
Major Milestones 09/15/15 PDR (Complete) 12/15/15 CDR (Complete) 6/15/16 System Integration Test 12/15/16 Flight Unit Vibe Test 6/15/17 Flight Unit Bakeout Test 9/15/17 MRR 10/15/17 Delivery 12/15/17 Launch on ELaNa XX Virgin Galactic |  | Size 1U | Mass 1.3 kg | RF Power 100mW
 |  | Deliverables Status RF License: Underway by Near Space Launch & GlobalStar 1616.25MHz ODAR: Initial version is underway NOAA: four CMOS imagers licensing underway MSPSP: from Virgin Galactic |  | 
 |  | Issues/Concerns Access to and cost of testing. Ultem plastic frame is unconventional. |  | 
MakerSat-0 is a mission to prepare for ISS-based fabrication, assembly, and deployment of CubeSats. MakerSat is designed so that its Ultem plastic frame rails can be 3D printed on the ISS Additive Manufacturing Facility and its six electronic board assemblies can be snapped into this frame by the ISS crew, and then deployed. However, MakerSat-0 will be ground built and tested. MakerSat is a multi-project satellite that provides four science teams the opportunity to fly their own science, while all power, computing, and radio communication tasks are provided by the core MakerSat system. These student teams will have 24/7 access to their science data via the GlobalStar satellite network downlink and EyeStar webpage.